## Slide 1: City of Burlingame Rain Garden

## Slide 2: Agenda
Location
Project History and Design
Rain Garden – parking lot
Drainage – storm runoff
Curb Extension – street runoff
Landscaping – California natives
Construction – changes in field
Financing - grant
Interpretive Sign
Lessons Learned

## Slide 3: Location – Downtown Burlingame
Project Location

## Slide 4: Project History and Design
Existing parking lot with on-street parking behind shopping district

## Slide 5: Public Parking Lot C

## Slide 6: Existing Conditions
Multiple driveways
Original landscaping

## Slide 7: Poor Drainage
Street runoff collects in gutter
Parking lot drainage ponds

## Slide 8: RAIN GARDEN
Reconfigure parking lot with two entrances and 90 degree stalls
Capture 16’ x 160’ area for bioswale
Design for 4’ wide channel at 5”-6” deep
California native landscaping
Irrigation for first few years only, by contractor choice
Two boardwalks for pedestrian access to parking lot

## Slide 9: Layout of Redesigned Parking Lot

## Slide 10: Rain Garden Photos

## Slide 11: STORM DRAINAGE
Captures runoff from commercial buildings and parking lot
1.32 acres of runoff equals 0.25 cfs for a 30 year event
Designed for 0.43 cfs – almost twice the required C3 guidelines
Overflow to curb for 50 to 100 year storm event

## Slide 12: Rain Garden - runoff

## Slide 13: Overflow to street

## Slide 14: Cross Sections

## Slide 15: CURB EXTENSION
Captures Runoff from Street and Parking Stalls
0.11 acres of runoff at 0.285 cfs – design for 0.33 cfs exceeding C3 guidelines.
Treats overflows from center cell of garden as well

## Slide 16: LANDSCAPING
All plants are California Natives
Includes Rush, Sedges, Carmel Creeper or Ceanothus, Iris, Barberry and Buckwheat
Tree specified was native Hackberrys - could not find and used Valley Oaks
Irrigation for first few years only -contractor installed as part of 6 month maintenance period
Use mulch that knits together not bark that floats
Valley Oak Trees
White flowering Ceanothus
Rushes and Sedges

## Slide 17: Landscape Plan

## Slide 18: CONSTRUCTION
• Demolition of parking lot
• Relocation of lights
• Restriping of parking

## Slide 19: Construction - continued
• Excavation
• Installation of rock
• Boardwalks
• Topsoil
• Landscaping
• Irrigation

## Slide 20: Financing
Grant from San Mateo County Storm Water Pollution Prevention
Cost – about $270,000 for design, engineering, and construction
Sustainable, Green Streets and Parking Lots program
Vehicle License Fees
Managed thru C/CAG

## Slide 21: Interpretive Sign
• Educating the public
• Staff designed sign
• Ordered from the Web

## Slide 22: Lesson Learned: Infiltration Test
Percolation test did not work
Infiltration test did
Works like toilet float
Three tests through
out the site

## Slide 23: Lesson Learned continued
Erosion along edge
Gutter debris into curb extension – use rock not pea gravel

## Slide 24: LESSONS LEARNED
Infiltration test for soil drainage
Added one foot rock strip to deter erosion
Enlarged rock storage area in swale
Include maintenance period and simple irrigation system
Check on plant availability
Contractor qualifications in specifications important

## Slide 25: Questions and Comments
Thank you